## Report
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS)
Work Breakdown Structure | Task Name | Total Budgeted Cost (TBC) | 1 | 2 | 3 | 4 | 5
1.1 | Brainstorm | 1000 | 500 | 500
1.2 | Project Management Plan | 2000 |  |  | 1500 |  | 500
1.3 | Application Development | 1500 |  |  |  | 1000 | 500
1.4 | Risk Management Plan | 1000 |  |  | 500 | 250 | 250
1.5 | Testing | 1500 |  |  |  | 1000 | 500
1.6 | Analysis | 1000 |  |  |  | 500 | 500
1.7 | Presentation/Documentation | 1000 |  |  |  |  | 1000
| Total Budgeted Cost | 9000 | 500 | 500 | 2000 | 2750 | 3250
|  | Cumulative Planned Value (PV) | 500 | 1000 | 3000 | 5750 | 9000
Actual Cost and Earned Value
|  | Cumulative Actual Cost (AC) | 500 | 500 | 3125 | 5450 | 7750
|  | Cumulative Earned Value (EV) | 1000 | 1000 | 3000 | 1825 | 3175
Project Performance Metrics
|  | Cost Variance (CV = EV - AC) | 500 | 500 | -125 | -3625 | -4575
|  | Schedule Variance (SV = EV - PV) | 500 | 0 | 0 | -3925 | -5825
|  | Cost Performance Index (CPI = EV/AC) | 2 | 2 | 0.96 | 0.33486 | 0.40968
|  | Schedule Performance Index (SPI = EV/PV) | 2 | 1 | 1 | 0.31739 | 0.35278
|  | Estimated Cost at Completion (EAC) | 4500 | 4500 | 9375 | 26876.7123 | 21968.5039

## Earned Value Sheet
Cumulative Earned Value (EV)
WBS | Task Name | TBC | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5
1.1 | Brainstorm | 1000 | 100% | 100%
1.2 | Project Management Plan | 2000 |  |  | 75% |  | 25%
1.3 | Application Development | 1500 |  |  |  | 66% | 34%
1.4 | Risk Management Plan | 1000 |  |  | 50% | 25% | 25%
1.5 | Testing | 1500 |  |  |  | 66% | 34%
1.6 | Analysis | 1000 |  |  |  | 50% | 50%
1.7 | Presentation/Documentation | 1000
|  | Cumulative EV | 1000 | 1000 | 2000 | 2730 | 2270

## Actual Cost Sheet
Actual Cost (AC) of Work Performed
WBS | Task Name |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5
1.1 | Brainstorm |  | 500 | 500
1.2 | Project Management Plan |  |  |  | 2000 |  | 400
1.3 | Application Development |  |  |  |  | 900 | 350
1.4 | Risk Management Plan |  |  |  | 625 | 250 | 250
1.5 | Testing |  |  |  |  | 900 | 400
1.6 | Analysis |  |  |  |  | 275 | 400
1.7 | Presentation/Documentation | [5 empty] | 500
|  | Total Actual Cost | 500 | 500 | 2625 | 2325 | 2300
|  | Cumulative Actual Cost (AC) | 500 | 1000 | 3625 | 5950 | 8250