## Sheet1
ID | Current Status | Risk Impact | Probability of Occurrence | Risk Description | Project Impact | Risk Area | Symptoms | Triggers | Risk Response Strategy | Response Strategy | Contingency Plan
1 | Closed | High | Low | Insufficient expertise or abilities among team members in particular areas needed for the project. | The quality of work may decrease and project milestones may be missed. | Project Resources | Difficulty completing activities or meeting deadlines owing to a lack of necessary abilities | Team members are available for collaborative development and meetings. | Mitigation | Find internal resource that meets required skill set or train existing resources | Provide training opportunities or resources to improve team members' skills.
2 | Open | Medium | Medium | Lack of clarity in communication may lead to misunderstanding of project objectives among team members. | Diverse efforts, rework, and probable project failure. | Project Management | Tasks are not consistently understood, and requirements vary frequently. | Ambiguous project paperwork and aims. | Avoidance | Develop clear project documentation, maintain a single source of truth for project objectives, and conduct regular alignment meetings. | If misalignment is found, schedule a project realignment session to verify that all team members are on the same page.
3 | Closed | Medium | High | Delays in obtaining the requisite API keys may delay data retrieval activities. | Potential delays in the project timeframe, influencing the total schedule. | Strategic | Inability to get API data causes project delays. | Delay in receiving API keys from providers. | Contingency | Initiate the API key request process early and follow up diligently. Have backup APIs as an alternative. | If API keys are not received on time, use alternative data sources or APIs.
4 | Closed | High | Medium | Selected platforms may not provide a public API for data retrieval. | Inability to incorporate specific platforms into the application. | Technology | Gaps in data collection capability. | Platforms are selected without first verifying API availability. | Contingency | Pre-project research to verify API availability and prepare manual data collection methods. | If no API is available, use other data collecting methods or modify the project scope.
5 | Closed | Medium | Low | Special characters in usernames create unhandled failures in API calls, resulting in failed data extraction. | Can result in insufficient data gathering and failure to satisfy project deliverables. | Technical Obsolescence | API requests failed, error messages appeared, and datasets were incomplete. | Using special characters in usernames. | Mitigation | Implement input validation and sanitization to handle special characters. Update error handling to manage such exceptions gracefully | Create a manual override system that allows administrators to retrieve data when automated retrieval fails.
6 | Closed | High | Medium | Dependencies that require higher versions of Python may result in environment incompatibility. | Environment reconfiguration causes development delays. | Technology | Errors during environment setup; failed builds. | Introduction of new dependencies that are incompatible with the present Python version. | Mitigation | Standardize development environment using Docker and virtual environments. | Have a consistent environment setup guide and help team members upgrade or configure their environments.
7 | Closed | High | Medium | APIs may be deprecated or their access restricted without prior notice. | Potential inability to retrieve data, leading to project delays and increased costs. | Data/Information | Sudden loss of data access and API problems. | Unannounced modifications to API policies or terms of service. | Mitigation | Regular monitoring of API status and establishing communication with API providers for updates. | Prepare a plan for local data storage or scraping as an alternative to API data retrieval.
8 | Open | Medium | Low | Misuse of internal APIs may result in the team's IP being blacklisted. | Loss of API access causes project delays or failure. | Overall Project Failure | Sudden inability to use APIs and receipt of ban warnings. | Exceeding API rate restrictions or breaking usage regulations. | Avoidance | Adhere strictly to API usage policies and implement rate limiting. | Use proxy servers or a VPN to rotate your IP address, If you are blocked.
9 | Open | High | High | Incompatibility issues between APIs | Delayed development, integration challenges | Dependencies/Interoperability | Application fails to retrieve data from APIs, inconsistent data processing | Changes in API endpoints or authentication methods | Mitigation | Develop adapters or middleware to handle data transformation between incompatible APIs. Conduct thorough testing to ensure compatibility. Keep account of API updates and changes | If incompatibility issues arise, consider alternative APIs or develop custom solutions to bridge the gap between incompatible APIs.
10 | Closed | Medium | Medium | Availability of skilled developers | Resource constraints, slowed progress | Project Resources | Difficulty finding developers proficient in the chosen language and GUI frameworks | Limited availability of skilled developers | Mitigation | Expand recruitment efforts to attract skilled developers. Offer training programs or educational resources to enhance existing team members' skills. Consider outsourcing certain tasks to fill skill gaps | If skilled developers are not available, prioritize critical tasks and redistribute workload among existing team members. Consider hiring freelancers or contracting external experts for specialized tasks
11 | Open | Medium | High | API rate limits and quota restrictions | Reduced functionality, degraded performance | Dependencies/Interoperability | Application fails to fetch data due to API rate limits | Increased user activity, popularity of the application | Mitigation | Implement request throttling and prioritize critical API requests. Monitor API usage and adjust request frequency accordingly. Explore options for increasing API quotas or obtaining premium access | If API rate limits are reached, adjust the application's behavior to handle rate limit errors gracefully. Implement caching mechanisms to reduce API requests
12 | Open | High | Low | Changes in API endpoints or authentication methods | Integration failures, data inconsistency | Dependencies/Interoperability | Application fails to authenticate or access API endpoints | API provider updates or deprecates endpoints | Mitigation | Regularly monitor API documentation for updates. Implement robust error handling and fallback mechanisms in case of API endpoint changes or authentication method updates. Maintain clear communication channels with API providers. | If API endpoints or authentication methods change, update the application's integration accordingly. Implement versioning strategies to handle backward compatibility issues
13 | Closed | Medium | Low | Delays in development due to unforeseen technical challenges | Schedule delays, missed milestones | Schedule | Unexpected technical hurdles arise during development | Complexity of integrating multiple APIs, lack of prior experience with chosen technology stack | Contingency | Allocate buffer time in the project schedule for handling unexpected technical challenges. Conduct regular code reviews and testing to identify potential issues early. Foster a culture of collaboration and knowledge sharing within the team | If unforeseen technical challenges arise, reassess project priorities and allocate resources accordingly. Seek external expertise or consulting if necessary
14 | Open | High | Medium | Security vulnerabilities in the application | Data breaches, loss of trust | Security | Unauthorized access to user data, data leakage | Inadequate security measures, lack of encryption | Mitigation | Implement regular security assessments and follow secure coding practices. Stay informed about security vulnerabilities and updates in relevant libraries and frameworks. Encourage responsible disclosure of security issues. | If security vulnerabilities are identified, immediately patch or mitigate them. Notify relevant stakeholders and users about the issue and provide guidance on protective measures.
15 | Open | Medium | Medium | Dependency on third-party libraries or services | Integration failures, compatibility issues | Dependencies/Interoperability | Application crashes or malfunctions due to incompatible library versions | Changes in third-party library APIs, updates, or deprecations | Mitigation | Have contingency plans for alternative libraries or services. Regularly update and patch dependencies to mitigate security risks. Monitor third-party library maintainers' activities and community feedback. | If a critical third-party library becomes unavailable or unreliable, assess the impact on the project and implement alternative solutions or develop in-house replacements if feasible.
18 | Open | Medium | High | Unforeseen changes in platform policies | Disruption of service, loss of access to APIs | Strategic | Application functionality affected by changes in platform policies | Updates or revisions to platform policies | Contingency | Regularly monitor platform announcements and updates. Maintain flexibility in project planning and development to accommodate potential policy changes. Establish contingency plans for adapting to platform policy changes. | If platform policies change unexpectedly, assess the impact on the project and adjust development strategies accordingly. Engage with platform administrators or support channels to seek clarification or guidance.
20 | Open | High | Low | Incompatibility issues between libraries and APIs may arise | Potential delays in integration and functionality of the application | Technology | Application fails to retrieve data from APIs or displays inaccurate information | Delays in obtaining access to necessary APIs or data sources | Mitigation | Develop adapters or middleware to handle data transformation between incompatible libraries and APIs. Stay informed about updates and changes in relevant libraries and APIs. Test compatibility thoroughly during development. | If incompatibility issues arise, explore alternative libraries or APIs that offer better compatibility. Implement fallback mechanisms or develop custom solutions to bridge compatibility gaps if feasible.